Module:  Tobacco-Free Colleges/Universities

Agency Name:

Project Name:

Program Goal : Eliminate Exposure to Secondhand Smoke

Objective: By September 2003 at least one college/university will develop and implement a tobacco-free policy

Key Strategies & activities


Needed

Resources
Person/group

responsible
Target date or timeline


Performance

Indicators

Community Interventions


1st Per
2nd Per
3rd Per


1. Identify college/university that is interested in working toward a tobacco-free policy, obtain a copy of the college/university tobacco policy, including the residence hall policy.
1. University contact, university web site (to obtain policy)
Coalition Coordinator or designated coalition member 


X


1. Copy of tobacco-free policies sent to MDCH consultant

2. Identify a contact person on-campus who will work on the tobacco-free campus project and assist in the development and facilitation of an on-campus student-led coalition.  Their goal is the development, implementation, and enforcement of a tobacco-free campus policy.



2. University/college student health center/services, administration, other faculty and staff


Coalition Coordinator or designated coalition member
X


2. Contact person information.

3. Assist the college/university facilitator in obtaining updated smoke-free college resource materials.
3. List of college resource guides.  List is included in your application and available from your consultant.
Coalition Coordinator

College/University facilitator


X


3. List of materials ordered.

4. Assist the college/university facilitator with forming an on-campus student coalition.

Ongoing recruitment.


4. On-campus student and faculty organizations, groups, and clubs, student athletes, other interested faculty, staff, and students, community organizations
Tobacco reduction coalition, college/university adult facilitator, students
X
X

On-campus student coalition is formed and list of members sent to MDCH.

Strategic Use of Media







1. Assist the college/university in developing an on-campus educational campaign on the health risks of secondhand smoke, benefits of clean indoor air, and how to quit tobacco use.


All on-campus media outlets, i.e., campus newspaper, radio, tv station, student union, health center, and other on-campus bulletin boards, student coalition fundraising events or college/university funding for media campaign
On-campus student coalition, college/university adult facilitator
X
X



2. Plan for and provide earned (free) media support for college/university tobacco-free policy through press releases, letters to the editor, and public service announcements.  


All local  media outlets for free media, media contacts

Designated earned media subcommittee 
Designated coalition member, on-campus earned media subcommittee


X
Copies of free media sent to MDCH.  



3. Assist the college/university in developing an on-campus  marketing campaign (financially supported by the college/university) to:

· promote the new tobacco-free policy and

· promote cessation services or referrals. 


All on-campus media outlets, i.e., campus newspaper, radio, tv station, student union, health center, and other on-campus bulletin boards, student coalition fundraising events or college/university funding for media campaign


On-campus student coalition


X
College media contact list is developed, contacts are made, and campaign progress, and copies of campaign materials are sent to MDCH.

Module:  Tobacco-Free Colleges/Universities

Agency Name:

Project Name:




Policy







1. The on-campus student coalition will complete or update a tobacco-free campus assessment to:

· recruit student and staff members 

· determine the status of the current campus policies,

· collect info on enforcement

· what tobacco prevention and cessation services or resources are provided to students

· determine support of on-campus tobacco-free events and policies from students and staff.
On-campus student coalition, copies of assessment tools from BAACHUS/GAMMA or CYAN, copies of campus policies; college/university student health services, administration, safety and planning committee, law enforcement, and other 

on-campus organizations


On-campus student coalition, college/university adult facilitator


X
X

Tobacco-free assessment completed and results sent to college/university administration and MDCH.



2. Assist the on-campus student coalition to identify a tobacco-free campus policy to work on during the 2003-2004 school year, such as smoke-free residence halls, on-campus designated smoking areas, eliminate tobacco sales and promotion on-campus, eliminate tobacco advertising on-campus, or implementing on-campus cessation services for students and staff.  For those coalitions in the second year of this project, the policy should be different from or building upon the prior-year’s policy.
Copies of other college/university tobacco-free policies, tobacco reduction coalition 
On-campus student coalition, adult facilitator, tobacco reduction coalition 
X


Tobacco-free policy is identified and developed and draft copy sent to MDCH.

3. Educate the college/university administration, faculty, staff and students on the health risks of secondhand smoke and benefits of clean indoor air as well as on the costs of repair, maintenance and insurance for smoking in residence halls.                                                                                                                                                                                                                                                                                                                                                                                                                                  
Tobacco Reduction Coalition, clean indoor air and secondhand smoke educational information
On-campus student coalition or education subcommittee
X
X

Summaries of educational presentations provided to MDCH

Module:  Tobacco-Free Colleges/Universities

Agency Name:

Project Name:
Surveillance and Evaluation







1. Use the completed college assessment tool to review progress over the past year.  Update the assessment tool to reflect progress/changes.
Campus tobacco reduction coalition
Completed assessment tool from beginning of the project.


X
Provide a copy of the revised assessment tool with your third period report.

1
6

